## 00 Start
PROJECT MANAGEMENT ¦ THE WORKING TOOLKIT
One project. Four stages. One controlled workbook. Use with the HR Delivery practitioner manual.
HR DELIVERY ¦ PRACTITIONER WORKBOOK | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
INITIATE > PLAN > IMPLEMENT > CLOSE
START WITH A CLEAN WORKING COPY The live forms and registers are intentionally blank. Fictional Project READY examples are isolated on EX Case and EX Calculations; they do not feed the live dashboard. Use 01 Setup first, then choose the tools your project needs.
SET UP YOUR PROJECT
FIND A TOOL / OPEN ITS TAB
REVIEW DELIVERY INDICATORS
CHECK STAGE-GATE EVIDENCE
LEARN FROM THE FICTIONAL CASE
CHECK THE SOURCE AND ADAPTATION RECORD
HOW TO WORK 1. Read the tool guide and example in the PDF. 2. Open the exact tab from 04 Tool Index. 3. Enter evidence in blue input cells. 4. Review calculated cells and warnings. 5. Obtain and reference the real approval. 6. Save a dated, versioned project copy. | IMPORTANT BOUNDARIES This is a single-project working template, not an approval system or multi-user database. B1 is a calendar-day tracker, not an automatic scheduling engine. Keep sensitive personal case material out of the workbook. No macros or external data connections are required.
DO NOT CONFUSE THESE A risk may happen; an issue has happened. A forecast predicts; an approved baseline records a commitment. Training attendance is not adoption. An output is not a benefit. Closing a project does not close the organisation's remaining responsibilities.
CAPACITY AND SAVING Core logs are prepared for 100 entries; specialist registers for 30. Use the workbook in a spreadsheet application that supports the included formulas and validation. Check the PDF instructions before extending any range. Save your copy locally after editing; the PDF is the printable guide and form reference.

## 01 Setup
01 ¦ PROJECT SETUP AND APPROVED CONTROLS
Project name |  | Use one project per working copy.
Project code |  | Stable reference for all records.
Project sponsor |  | Name the authorised sponsor.
Project manager |  | Name the person coordinating delivery.
Status date |  | Enter a real date; overdue indicators use this date, not TODAY().
Reporting currency | SAR | SAR is an editable example, not a fixed requirement.
Original planned close |  | Preserve the original approved completion date.
Approved cost tolerance |  | Enter a percentage, e.g. 5%; obtain approval before use.
Approved time tolerance |  | Enter calendar days; do not silently convert a source month to 30 days.
Project start |  | Used as the first week anchor on B1 Gantt.
Current approved close |  | Update only with authorised change; preserve row 10.
Baseline version |  | Identify the currently approved plan.
Approval evidence |  | Reference the actual delegated approval; this workbook cannot authenticate it.
Reporting period from |  | Start of the period covered by C1.
Reporting period to |  | End of the period covered by C1.
Overall status judgement | Not assessed | Human judgement: indicators do not overrule mandatory conditions.
Decision / status reason |  | Explain the judgement and decision needed.
Reserve owner |  | Who may authorise release of contingency?
Funding authority |  | Record the applicable organisational authority.
Operational owner |  | Who will run the result after handover?
Information owner |  | Who reviews access, retention and information use?
Original cost baseline
Complete approved changes
Current approved budget
Complete forecast total
Forecast variance
CONTROL NOTE ¦ The source includes example tolerances. This live template leaves tolerance approval to the project. Do not interpret a blank limit as zero or unlimited authority. Baseline, forecast and actual are different records. Save a dated working copy before entering project data.
CAPACITY ¦ Core logs have 100 prepared rows (10-109). Other specialist registers have 30 rows. Formulas and dashboard ranges cover these prepared rows only. A larger project needs a controlled extension of tables, formulas, validations and dashboard references.

## 02 Dashboard
02 ¦ PROJECT DELIVERY DASHBOARD
Evidence-led indicators. Overall RAG remains an authorised human judgement.
HR DELIVERY ¦ PRACTITIONER WORKBOOK |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
LIVE PROJECT ¦ No fictional examples are included in these calculations.
Project | NOT CONFIGURED | READ BEFORE INTERPRETING
Status date | NOT SET
Reported tasks | NO TASKS ENTERED
Open issues | NO ISSUES ENTERED | No entries means no recorded evidence, not no exposure. A zero count can only be interpreted after checking completeness. Review data warnings and mandatory safeguards before judging delivery. Cost indicators require the baseline and all cost lines to be reconciled. Blank forecasts are not zero cost.
High / Extreme open risks | NO RISKS ENTERED
Pending change requests | NO CHANGES ENTERED
Overdue open actions | STATUS DATE REQUIRED
Unaccepted test records | NO TESTS ENTERED
Overall judgement | Not assessed
Schedule data warnings | 0
Cost-record warnings | 0
Incomplete change approvals | 0
Unrated / invalid risks | 0
Cost position | Amount (SAR) | Task status | Count | Open risk category | Count
Original baseline |  | Complete | 0 | Low | 0
Current approved |  | In progress | 0 | Moderate | 0
Forecast |  | Not started | 0 | High | 0
Variance to current |  | Forecast late | 0 | Extreme | 0
|  | Overdue | 0
|  | Other / missing | 0
REVIEW ROUTE Check the status date. Read the C1 narrative. Resolve missing records. Consider consequences, not just counts. Record the decision in C7. Change the baseline only through approved C2/C2B records.
NO AUTOMATIC GREEN These charts show entries in the workbook. They do not prove delivery, safety, compliance, acceptance or benefit realisation. Review supporting evidence and use the project's approved escalation rules.

## 03 Gates
03 ¦ STAGE-GATE CONTROL
An evidence checklist supports the decision; it never grants authority.
HR DELIVERY ¦ PRACTITIONER WORKBOOK | [5 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Gate | Criterion | Mandatory? | Evidence reference | Owner / reviewer | Check status | Decision / condition | Due date
G1 | Sponsor and authority identified | Yes |  |  | Not assessed
G1 | Problem, scope and exclusions agreed | Yes |  |  | Not assessed
G1 | Business case includes credible alternatives | Yes |  |  | Not assessed
G1 | Planning resource and decision conditions recorded | Yes |  |  | Not assessed
G2 | Accepted outputs and tests defined | Yes |  |  | Not assessed
G2 | Schedule, budget and capacity reconciled | Yes |  |  | Not assessed
G2 | Risk and information safeguards agreed | Yes |  |  | Not assessed
G2 | Transition and benefits owners accept commitments | Yes |  |  | Not assessed
G3 | Release conditions and mandatory tests satisfied | Yes |  |  | Not assessed
G3 | Output acceptance and support evidence recorded | Yes |  |  | Not assessed
G3 | Residual exposure identified with receiving owners | Yes |  |  | Not assessed
G3 | Completion evidence and closure route agreed | Yes |  |  | Not assessed
G4 | Completion report and Finance position accepted | Yes |  |  | Not assessed
G4 | Residual transfers and benefits reviews accepted | Yes |  |  | Not assessed
G4 | Records, access and resources accounted for | Yes |  |  | Not assessed
G4 | Authorised closure decision recorded | Yes |  |  | Not assessed
Gate | Passed / applicable | Checklist progress | Evidence gaps | Control interpretation
G1 | 0 | 0% | 0 | MANDATORY HOLD
G2 | 0 | 0% | 0 | MANDATORY HOLD
G3 | 0 | 0% | 0 | MANDATORY HOLD
G4 | 0 | 0% | 0 | MANDATORY HOLD
DECISION RECORD ¦ Use A14, B22, C21 and D14 for the actual gate papers. A tick, date, typed name or 100% checklist is not an electronic signature or delegated approval. Mandatory checks cannot be waived by marking them Not applicable; revise the agreed control explicitly with authority.

## 04 Tool Index
04 ¦ MASTER TOOL INDEX
Open a tool from its linked name. PDF page references point to the guide, form and example.
HR DELIVERY ¦ PRACTITIONER WORKBOOK |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Code | Stage | Tool / linked tab | Guide page | Form page | Example page | Type | Core route? | Source basis
A1 | Project initiation | Project brief | 30 | 31 | 32 | canvas | Yes | Adapted from S04, A1; S03, slides 15-16.
A2 | Project initiation | Business case | 33 | 34 | 36 | canvas | Yes | Adapted from S04, A2; external context R01.
A3 | Project initiation | Project initiation document (PID) | 38 | 39 | 41 | canvas | Yes | Adapted from S04, A3; S03, slides 19-25.
A4 | Project initiation | Sponsor agreement and governance | 43 | 44 | 45 | canvas | Yes | Developed from S04, PID governance; HR Delivery addition.
A5 | Project initiation | Problem and opportunity evidence | 46 | 47 | 48 | canvas | Optional / contextual | HR Delivery development
A6 | Project initiation | Stakeholder analysis | 49 | 50 | 51 | canvas | Optional / contextual | Adapted from S05, communications stakeholder map; HR Delivery impact safeguard.
A7 | Project initiation | Scope and requirements boundary | 52 | 53 | 54 | canvas | Optional / contextual | Adapted from S04, business case and PID scope classifications.
A8 | Project initiation | Options appraisal | 55 | 56 | 57 | matrix | Optional / contextual | Developed from S04, A2 options appraisal; HR Delivery weighted calculation.
A9 | Project initiation | Complexity and assurance assessment | 58 | 59 | 60 | canvas | Optional / contextual | Developed from S04, A1 complexity; HR Delivery assurance additions.
A10 | Project initiation | Assumptions and dependencies register | 61 | 62 | 63 | register | Optional / contextual | HR Delivery development
A11 | Project initiation | Initial estimate and funding request | 64 | 65 | 66 | canvas | Optional / contextual | Adapted from S04, outline costs and business case; HR Delivery cost controls.
A12 | Project initiation | Success measures and baseline | 67 | 68 | 69 | canvas | Yes | HR Delivery development
A13 | Project initiation | Initiation workshop | 70 | 71 | 72 | script | Optional / contextual | HR Delivery development
A14 | Project initiation | Gate 1: authorise project planning | 73 | 74 | 75 | gate | Yes | HR Delivery development
B1 | Project planning | Project schedule and Gantt tracker | 86 | 87 | 88 | register | Yes | Adapted from S08, Schedule Tracker; S03, slides 30-32. Scheduling context R03.
B2 | Project planning | Project communications plan | 89 | 90 | 91 | register | Yes | Adapted from S05, B2.
B3 | Project planning | Output description and acceptance specification | 92 | 93 | 94 | canvas | Yes | Adapted from S05, B3 output descriptions.
B4 | Project planning | Benefits realisation plan | 95 | 96 | 97 | register | Yes | Adapted from S05, B4; S03, slide 28.
B5 | Project planning | Transition plan | 98 | 99 | 100 | canvas | Yes | Adapted from S05, B5; earlier S01 labels this B6. This edition follows S02/S05.
B6 | Project planning | Project contact list | 101 | 102 | 103 | register | Optional / contextual | Developed from S07, contact checklist under D3; source discrepancy in S05 B6 recorded.
B7 | Project planning | Work breakdown structure | 104 | 105 | 106 | canvas | Optional / contextual | HR Delivery development
B8 | Project planning | Dependency network and critical path | 107 | 108 | 109 | matrix | Optional / contextual | Developed from S03, slides 31-32; calculation by HR Delivery. Context R03.
B9 | Project planning | Resource and capacity plan | 110 | 111 | 112 | register | Optional / contextual | HR Delivery development
B10 | Project planning | Project budget and cost baseline | 113 | 114 | 115 | register | Yes | Developed from S04, project costs and budget; HR Delivery calculation architecture.
B11 | Project planning | Responsibility assignment matrix (RACI) | 116 | 117 | 118 | matrix | Optional / contextual | HR Delivery development
B12 | Project planning | Quality and acceptance plan | 119 | 120 | 121 | register | Yes | Developed from S04 PID quality and S05 output quality fields.
B13 | Project planning | Requirements-to-acceptance traceability | 122 | 123 | 124 | register | Optional / contextual | HR Delivery development
B14 | Project planning | Procurement and supplier plan | 125 | 126 | 127 | canvas | Optional / contextual | HR Delivery development
B15 | Project planning | Change-control procedure | 128 | 129 | 130 | canvas | Yes | Developed from S06 C2 and S09; external context R02.
B16 | Project planning | Risk workshop and response plan | 131 | 132 | 133 | script | Optional / contextual | Developed from S03, slides 39-44 and S11 risk log.
B17 | Project planning | Project information-handling plan | 134 | 135 | 136 | canvas | Optional / contextual | HR Delivery development
B18 | Project planning | Adoption and learning plan | 137 | 138 | 139 | canvas | Optional / contextual | HR Delivery development
B19 | Project planning | Planning assumptions challenge | 140 | 141 | 142 | canvas | Optional / contextual | HR Delivery development
B20 | Project planning | Contingency and scenario plan | 143 | 144 | 145 | canvas | Optional / contextual | HR Delivery development
B21 | Project planning | Integrated baseline review | 146 | 147 | 148 | canvas | Yes | HR Delivery development
B22 | Project planning | Gate 2: authorise implementation | 149 | 150 | 151 | gate | Yes | HR Delivery development
C1 | Project implementation | Project progress report | 162 | 163 | 164 | canvas | Yes | Adapted from S06, C1 progress-report template; C5 source example treated separately.
C2 | Project implementation | Project change request | 165 | 166 | 168 | canvas | Yes | Adapted from S06, C2; S09 change-log fields. Context R02.
C2B | Project implementation | Project change log | 170 | 171 | 172 | register | Yes | Adapted from S09, Change Log; HR Delivery approval-integrity additions.
C3 | Project implementation | Project issues log | 173 | 174 | 175 | register | Yes | Adapted from S10, Issue Log; S03, slides 39, 47-48.
C4 | Project implementation | Project risk log | 176 | 177 | 178 | register | Yes | Adapted from S11, Risk Log; S03, slide 44 matrix.
C5 | Project implementation | Project progress report: worked-report clinic | 179 | 180 | 181 | canvas | Optional / contextual | Developed from S06, duplicate C1/C5 and worked example; HR Delivery review method.
C6 | Project implementation | Project action log | 182 | 183 | 184 | register | Optional / contextual | HR Delivery development
C7 | Project implementation | Project decision log | 185 | 186 | 187 | register | Optional / contextual | HR Delivery development
C8 | Project implementation | Milestone and delivery review | 188 | 189 | 190 | register | Optional / contextual | HR Delivery development
C9 | Project implementation | Cost forecast and commitments | 191 | 192 | 193 | register | Yes | HR Delivery development
C10 | Project implementation | Integrated change-impact assessment | 194 | 195 | 196 | canvas | Optional / contextual | HR Delivery development
C11 | Project implementation | Quality test and defect log | 197 | 198 | 199 | register | Yes | HR Delivery development
C12 | Project implementation | Supplier performance review | 200 | 201 | 202 | canvas | Optional / contextual | HR Delivery development
C13 | Project implementation | Project team meeting and minutes | 203 | 204 | 205 | script | Optional / contextual | HR Delivery development
C14 | Project implementation | Stakeholder engagement review | 206 | 207 | 208 | canvas | Optional / contextual | HR Delivery development
C15 | Project implementation | Adoption and learning tracker | 209 | 210 | 211 | register | Optional / contextual | HR Delivery development
C16 | Project implementation | Exception and recovery plan | 212 | 213 | 214 | canvas | Yes | HR Delivery development
C17 | Project implementation | Pilot and release-readiness review | 215 | 216 | 217 | gate | Yes | HR Delivery development
C18 | Project implementation | Go-live, cutover and rollback plan | 218 | 219 | 220 | register | Optional / contextual | HR Delivery development
C19 | Project implementation | Operational handover and acceptance | 221 | 222 | 223 | canvas | Yes | Developed from S05 B5, S07 D1 and S03 slides 54-57.
C20 | Project implementation | Benefits and business-case review | 224 | 225 | 226 | canvas | Optional / contextual | HR Delivery development
C21 | Project implementation | Gate 3: authorise closure preparation | 227 | 228 | 229 | gate | Yes | HR Delivery development
D1 | Project close | Project completion report | 237 | 238 | 240 | canvas | Yes | Adapted from S07, D1; HR Delivery original/revised baseline comparison.
D2 | Project close | Lessons learnt record | 242 | 243 | 244 | register | Yes | Original HR Delivery form developing S07 D2 heading and S03 closure learning.
D3 | Project close | Stakeholder management for successful implementation | 245 | 246 | 247 | canvas | Optional / contextual | Retains S02/S07 D3 title; developed method by HR Delivery.
D4 | Project close | Project managing the HR strategy implementation | 248 | 249 | 250 | canvas | Optional / contextual | Retains S02/S07 D4 title; original HR Delivery development.
D5 | Project close | Final acceptance and sign-off | 251 | 252 | 253 | canvas | Yes | Developed from S05 B5 acceptance and S07 D1 approval.
D6 | Project close | Financial reconciliation and closure | 254 | 255 | 256 | register | Yes | HR Delivery development
D7 | Project close | Residual risks, issues and actions transfer | 257 | 258 | 259 | register | Yes | Developed from S07 D1 open risks/issues and S05 B5 transition.
D8 | Project close | Benefits ownership and follow-up | 260 | 261 | 262 | canvas | Yes | HR Delivery development
D9 | Project close | Project archive and information disposal | 263 | 264 | 265 | canvas | Optional / contextual | HR Delivery development
D10 | Project close | Resource and supplier release | 266 | 267 | 268 | canvas | Optional / contextual | HR Delivery development
D11 | Project close | Project closure and learning workshop | 269 | 270 | 271 | script | Optional / contextual | HR Delivery development
D12 | Project close | Post-implementation review | 272 | 273 | 274 | canvas | Optional / contextual | HR Delivery development
D13 | Project close | Premature closure and stop decision | 275 | 276 | 277 | canvas | Optional / contextual | HR Delivery development
D14 | Project close | Gate 4: close and transfer accountability | 278 | 279 | 280 | gate | Yes | HR Delivery development

## 05 Source Map
05 ¦ SOURCE AND ADAPTATION MAP
Source-derived terminology is retained. New controls and examples are identified rather than attributed to the source.
HR DELIVERY ¦ PRACTITIONER WORKBOOK |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Topic / code | Source | Adopted location | Editorial treatment / source limitation
Four-stage structure | S01 / S02 / S03 | A Initiation; B Planning; C Implementation; D Close | Stage names retained. Four gates, routes and added tools are HR Delivery developments.
A1 / A2 / A3 | S04 | A1 / A2 / A3 | Core headings retained and made usable with decision evidence, examples and workbook forms.
Transition and contacts numbering | S01 versus S02/S05 | B5 Transition / B6 Contacts | Use S02 numbering consistent with the planning headings. Earlier B6/B7 remain source aliases, not extra tools.
B6 source content mismatch | S05 B6; S07 D3 | B6 Contacts | Planning B6 repeats transition text. Contact checklist in close collection supplies the starting fields; the expanded directory is original.
C1 and C5 duplicate title | S01 / S02 / S06 | C1 live form; C5 report clinic | Retain both IDs but distinguish their purpose. C5 is a worked-report review, not a second competing live report.
C2B spreadsheet | S09 / S06 | C2B Change Log | Preserve source fields; add approval completeness and verified implementation controls.
D2 heading only | S07 | D2 Lessons | Full working record, script and adoption checks are HR Delivery development; not attributed to missing source content.
D3 heading plus contacts | S02 / S07 | D3 Stakeholder Handover | Retain title; develop a closing relationship-transfer tool. Contact checklist also informs B6.
D4 heading only | S02 / S07 | D4 Strategy Handover | Retain title; strategic linkage and next-work classification are original development.
Risk categories and labels | S03 slide 44; S11 | B16 / C4 / 06 Lists | Retain the supplied 5x5 labels and category pattern. Contextual anchors, controls and residual checks are explicit additions.
Source tolerance examples | S04 A1 | A3 / 01 Setup | Source examples of 5% cost and one month are not universal defaults. Users must enter and approve project-specific limits.
Healthcare-specific examples | S03-S07 | Across this manual | Adapt role labels for corporate HR/OD use. The new RTS case is fictional and is not evidence about the source organisations.
Legacy spreadsheet format | S08-S11 | One .xlsx workbook | Rebuilt as one workbook with separate indexed tabs. No macros or legacy embedded objects are carried over.
Additional practitioner controls | HR Delivery development | A4-A14; B7-B22; C6-C21; D5-D14 | Original expansions make the core lifecycle practical. They are not claimed to be verbatim source templates.
ID | Source title | Type | How used | Source / URL
S01 | Overall Framework HRPM.pptx | Supplied framework, 2 slides | Four stages and initial tool families; planning aliases B6 Transition and B7 Contacts. | User-supplied source
S02 | HR Project Framework.pptx | Supplied framework, 1 slide | Controlling tool numbering for B5 Transition, B6 Contacts and D1-D4. | User-supplied source
S03 | Slides - Project Management- 2nd draft-11012020-BR.pptx | Supplied training, 60 slides | Lifecycle, project-manager responsibilities, planning, critical path, risk matrix, changes and close. | User-supplied source
S04 | Project_Initiation(1).docx | Supplied initiation collection | A1 brief, A2 business case and A3 PID; source-specific examples generalised for this toolkit. | User-supplied source
S05 | Project Planning.docx | Supplied planning collection | Communications, outputs, benefits and transition. B6 heading is followed by repeated transition content. | User-supplied source
S06 | PROJECT IMPLEMENTATION.docx | Supplied implementation collection | C1/C5 progress versions and example; C2 change request and C2B change-log reproduction. | User-supplied source
S07 | Project_Close(1).docx | Supplied close collection | D1 completion report; D2/D4 headings; D3 heading and contact checklist. | User-supplied source
S08 | B1 - Project Schedule.xls | Supplied legacy workbook | Schedule Tracker: ID, Action, Dependency, Duration, planned/actual dates, Owner and Status. | User-supplied source; original filename uses an en dash
S09 | C2(B)Project_Change_Log_Template(1).xls | Supplied legacy workbook | Change Log fields, status options and document control. | User-supplied source
S10 | C3 - Project Issues Log.xls | Supplied legacy workbook | Issue, impact, actions, owner, escalation, resolution and closure dates. | User-supplied source; original filename uses an en dash
S11 | C4 - Project Risk Log.xls | Supplied legacy workbook | Impact, likelihood, matrix, proximity, response, owner and review/closure fields. | User-supplied source; original filename uses an en dash
T01 | HR Delivery EDDIE Consultancy Toolkit - Second Edition | Presentation reference, 413 pages | Structure, two-column guides, tool codes, front and stage indexes, forms, examples and navigation. | User-approved presentation template
R01 | Association for Project Management: What is a business case? | External professional context | Used for concise context on business-case justification and continuing ownership, not to replace the supplied structure. | https://www.apm.org.uk/resources/what-is-project-management/what-is-a-business-case/
R02 | Association for Project Management: What is change control? | External professional context | Used for concise context on capturing, evaluating, deciding and controlling changes. | https://www.apm.org.uk/resources/what-is-project-management/what-is-change-control/
R03 | US Government Accountability Office: Schedule Assessment Guide, GAO-16-89G | External scheduling context, 2015 | Used for concise context on schedule logic, baseline integrity and credibility. Worked calculations are original teaching examples. | https://www.gao.gov/products/gao-16-89g

## 06 Lists
06 ¦ DEFINITIONS AND CONTROL LISTS
Risk category threshold | Value
Low maximum score | 3 |  |  | OPEN TOOL INDEX
Moderate maximum score | 6
High maximum score | 12
Minimum valid rating | 1
Maximum valid rating | 5
Due-soon window (days) | 7
Weekly chart interval (days) | 7
Rating | Impact label | Likelihood label | Use
1 | Negligible | Rare | Contextualise before rating
2 | Minor | Unlikely | Ordinal judgement, not probability
3 | Moderate | Possible | Use evidence and qualified judgement
4 | Major | Likely | Review severe consequences separately
5 | Catastrophic | Almost Certain | Mandatory safeguards can override score
SOURCE MATRIX ¦ The supplied training slide 44 uses Low, Moderate, High and Extreme. With valid integer impact and likelihood ratings 1-5, products 1-3 are Low, 4-6 Moderate, 8-12 High and 15-25 Extreme. The gaps are products that cannot occur. A score is not an expected loss or a failure probability.
DATA CONVENTIONS ¦ Date fields are real Excel dates. Percentages are decimals: 0.85 displays as 85%. An empty input means not supplied; enter 0 only when zero is the correct observation. No automatic overall Green rating is produced.
COST CONVENTION ¦ Forecast at completion = actual recognised cost + unpaid committed cost not already in actuals + other uncommitted estimate to complete. Include each amount once. Finance confirms the applicable accounting treatment.
SOURCE CONTROL ¦ S03 slide 44 and S11 supply risk labels/fields. Formulas, integrity checks, residual assessment, example values and dashboard architecture are HR Delivery developments. Source numbering variations are documented in 05 Source Map.

## A1 Project Brief
A1 ¦ Project brief
Agree the initial purpose, boundaries and authority for the proposed project.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S04, A1; S03, slides 15-16.
01 ¦ Purpose and strategic fit
Describe the need, evidence and organisational priority.
02 ¦ Objectives and success
State the result, beneficiary and observable measure.
03 ¦ Scope and exclusions
Identify locations, people, outputs and what is not included.
04 ¦ Outline case
Summarise benefits, do-nothing implications, cost range and duration.
05 ¦ Complexity and exposure
Record stakeholder, contract and technical complexity; major risks and dependencies.
06 ¦ Authority and next step
Name sponsor, project manager, approval decision, conditions and planning allowance.
COMPLETION CHECK ¦ An approved brief authorises the agreed next step only. The source includes illustrative cost and time tolerances; these are not universal approval limits. Record the local authority and actual tolerances explicitly.
NEXT RECORD ¦ A2 Business Case / A3 PID

## A2 Business Case
A2 ¦ Business case
Make a defensible choice between alternatives and justify the investment.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S04, A2; external context R01.
01 ¦ Executive recommendation
State the option, amount sought and decision required.
02 ¦ Strategic fit and need
Connect evidence, objectives and organisational priorities.
03 ¦ Options appraisal
Compare do nothing and viable alternatives on benefits, costs, time and risk.
04 ¦ Preferred scope and approach
Define outputs, boundaries and the delivery approach.
05 ¦ Benefits and measurement
Identify benefit type, baseline, target, owner and review date.
06 ¦ Costs and affordability
Separate one-off, ongoing, internal effort and contingency.
07 ¦ Risks and assumptions
Identify critical uncertainties and sensitivity of the recommendation.
08 ¦ Resources and stakeholders
Name commitments, delivery skills, decision makers and affected users.
09 ¦ Approval and review
Record the sponsor, conditions, validity date and review triggers.
COMPLETION CHECK ¦ Do not count the same benefit twice, treat released hours as automatic payroll savings, or conceal implementation costs. The source structure is retained; sensitivity and benefit-classification checks are HR Delivery additions.
NEXT RECORD ¦ A8 Options / A11 Estimate / G1

## A3 PID
A3 ¦ Project initiation document (PID)
Establish the controlled reference for what the project will deliver and how it will be governed.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S04, A3; S03, slides 19-25.
01 ¦ Aim, objectives and approach
Describe the result and overall method.
02 ¦ Scope classification
Record Must Have, Should Have, Could Have and Will not Have.
03 ¦ Benefits and stakeholders
Name users, benefit owners and measures.
04 ¦ Quality, acceptance and standards
Specify criteria, reviewers, mandatory standards and evidence.
05 ¦ Governance and reporting
Name sponsor, board, manager, team and reporting rhythm.
06 ¦ Plan and dependencies
Reference outputs, prerequisites, schedule and external commitments.
07 ¦ Budget and resources
Reference the estimate, funding and internal capacity commitments.
08 ¦ Tolerances and change
State authority limits, escalation and change procedure.
09 ¦ Output ownership and control
Name the receiving owners, approved versions and sign-off.
COMPLETION CHECK ¦ The source places the first PID in initiation and updates it during planning and implementation. Preserve that lifecycle. Do not treat a draft schedule attached to an early PID as an approved implementation baseline.
NEXT RECORD ¦ B21 Integrated Review / B22 G2

## A4 Governance
A4 ¦ Sponsor agreement and governance
Clarify sponsorship, delegated decisions and escalation before the project gathers momentum.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S04, PID governance; HR Delivery addition.
01 ¦ Sponsor commitment
Record purpose, availability and resource responsibilities.
02 ¦ Key roles
Name sponsor, business owner, project manager, accepters and assurance.
03 ¦ Decision rights
Define decisions, delegates and non-delegable conditions.
04 ¦ Forums and cadence
Set meeting purpose, membership and evidence deadlines.
05 ¦ Escalation and cover
Define triggers, response expectations and deputies.
06 ¦ Agreement and review
Record approval, unresolved authority gaps and review date.
COMPLETION CHECK ¦ Do not invent financial authority or assume a title confers it. This record is an operating agreement subject to the organisation's actual delegations, not a substitute for them.
NEXT RECORD ¦ A3 PID / C7 Decisions

## A5 Evidence
A5 ¦ Problem and opportunity evidence
Define the need without assuming that the requested solution is the answer.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Observed gap
Record the result, period, population and denominator.
02 ¦ User experience
Describe the effect on employees, managers or customers.
03 ¦ Evidence register
List source, date, reliability and limits.
04 ¦ Explanations to test
Separate competing hypotheses from established facts.
05 ¦ Strengths to preserve
Identify practices that should not be damaged.
06 ¦ Decision implication
State what is known, unknown and needed next.
COMPLETION CHECK ¦ Anecdotes can identify useful questions but do not establish prevalence. Do not label a person or department as the cause without investigating the system and checking contrary evidence.
NEXT RECORD ¦ A1 Brief / A12 Baseline

## A6 Stakeholders
A6 ¦ Stakeholder analysis
Identify affected people, decision influence and the engagement each group needs.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S05, communications stakeholder map; HR Delivery impact safeguard.
01 ¦ Group and stake
Name the group, interest and effect of the change.
02 ¦ Influence and interest
Record high/low judgements and evidence.
03 ¦ Engagement approach
Select Manage, Satisfy, Inform or Monitor with reasons.
04 ¦ Concerns and access
Identify needs, language, shift patterns and constraints.
05 ¦ Contribution and owner
State the required input and relationship owner.
06 ¦ Review and changes
Record validation and the next review trigger.
COMPLETION CHECK ¦ Low influence is not permission to ignore someone materially affected. Keep sensitive opinions out of widely circulated contact lists; describe observable concerns rather than labelling people resistant.
NEXT RECORD ¦ B2 Communications / B6 Contacts

## A7 Scope
A7 ¦ Scope and requirements boundary
Make the project boundary visible and prevent unapproved expansion.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S04, business case and PID scope classifications.
01 ¦ In-scope result
Name outcomes and output families.
02 ¦ Requirements classification
List Must, Should, Could and Will not Have items.
03 ¦ Explicit exclusions
Describe excluded functions, populations and changes.
04 ¦ Interfaces
Identify neighbouring work and handover responsibilities.
05 ¦ Acceptance boundary
State the minimum viable and acceptable result.
06 ¦ Change rule
Record baseline version, approver and escalation route.
COMPLETION CHECK ¦ Must Have should mean the result is not viable or acceptable without it. Record why. A scope list without acceptance criteria or an authorised owner does not protect the project.
NEXT RECORD ¦ B3 Outputs / B13 Traceability

## A8 Options
A8 ¦ Options appraisal
Compare credible alternatives using explicit criteria and test the recommendation.
01 ¦ PROJECT INITIATION |  |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S04, A2 options appraisal; HR Delivery weighted calculation.
Agree weights before scoring. Defaults below are illustrative; they must total 100%.
Option | Mandatory condition | Benefit | Deliverability | Affordability | Manageable risk | Weighted score
WEIGHTS |  | 35% | 25% | 20% | 20% | WEIGHTS OK
DECISION NOTE ¦ A score is one input, not approval. Record score evidence, sensitivity and the authorised decision below. The mandatory test is separate; a failed or unconfirmed condition prevents a numerical recommendation.
Evidence, sensitivity and decision rationale

## A9 Assurance
A9 ¦ Complexity and assurance assessment
Scale the project controls to uncertainty, consequence and organisational capacity.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S04, A1 complexity; HR Delivery assurance additions.
01 ¦ Complexity profile
Describe stakeholder, contract and technical complexity.
02 ¦ Consequence and novelty
Identify failure impact and unfamiliar work.
03 ¦ Capacity and competence
Check available skills, time and decision support.
04 ¦ Mandatory reviews
Name specialist checks and release constraints.
05 ¦ Assurance plan
Set proportionate gates, reporting and independent review.
06 ¦ Tailoring approval
Record rationale, approver and reassessment triggers.
COMPLETION CHECK ¦ This is a practice judgement, not a validated psychometric instrument. Do not average away a severe safety, legal or information-handling consequence. A single critical condition can require stronger assurance.
NEXT RECORD ¦ B12 Quality / B17 Information / gate reviews

## A10 Assumptions
A10 ¦ Assumptions and dependencies register
Expose what the project relies on and convert uncertainty into an owned test or commitment.
01 ¦ PROJECT INITIATION |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
ID / type | Assumption or dependency | Evidence / commitment | Owner | Required by | Status / action
USE THE RECORD ¦ What are we relying on without confirmation? Who supplies it? When does uncertainty become an immediate delivery problem? Do not call a dependency agreed merely because it appears in your own plan. Link any resulting risk, issue or change; closing the assumption record must not hide the resulting action.

## A11 Estimate
A11 ¦ Initial estimate and funding request
Build an honest estimate and identify the authority needed for funding.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S04, outline costs and business case; HR Delivery cost controls.
01 ¦ Estimate boundary
Define currency, period, outputs and exclusions.
02 ¦ Cost breakdown
List quantities, rates and estimate basis.
03 ¦ Internal capacity
Include effort and opportunity cost where relevant.
04 ¦ Uncertainty and reserve
Record range, contingency and release rules.
05 ¦ Funding request
State the amount, source and approval conditions.
06 ¦ Review and ownership
Name estimate owner, Finance reviewer and next update.
COMPLETION CHECK ¦ Contingency is not spare money to absorb any request. Do not spend it without authority or count it again inside every work package. Keep funding, forecast and actual expenditure distinct.
NEXT RECORD ¦ B10 Budget / C9 Forecast

## A12 Measures
A12 ¦ Success measures and baseline
Define success before implementation and establish a comparable starting point.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Measure and type
Identify output, outcome or balancing measure.
02 ¦ Operational definition
Specify unit, numerator, denominator and exclusions.
03 ¦ Baseline
Record value, date, population, source and limitations.
04 ¦ Target and rationale
State the intended change and why it is reasonable.
05 ¦ Ownership and review
Name data owner, benefit owner and review date.
06 ¦ Interpretation safeguards
Record missing data, comparability and unintended effects.
COMPLETION CHECK ¦ A target is a project commitment, not a benchmark unless a defensible benchmark exists. Avoid causal claims from before-and-after figures alone; record other changes and measurement differences.
NEXT RECORD ¦ B4 Benefits / C20 Review / D8 Ownership

## A13 Initiation Workshop
A13 ¦ Initiation workshop
Run a focused conversation that produces an agreed project proposition and unresolved decisions.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Purpose and participants
Record the decision, authority and required voices.
02 ¦ Evidence and objectives
Capture agreed need, target and competing interpretations.
03 ¦ Scope and output agreement
Record inclusions, exclusions, users and acceptance.
04 ¦ Resources and uncertainty
List capacity gaps, assumptions, risks and dependencies.
05 ¦ Decisions and conditions
Distinguish agreement, recommendation and formal approval.
06 ¦ Actions and read-back
Assign owner, due date, record location and next gate.
COMPLETION CHECK ¦ Do not report agreement because nobody objected. Ask each accountable owner to state their commitment and record dissent or unresolved conditions accurately.
NEXT RECORD ¦ A1 Brief / A14 G1

## A14 G1 Planning Gate
A14 ¦ Gate 1: authorise project planning
Make an explicit decision to proceed, proceed with conditions, return or stop.
01 ¦ PROJECT INITIATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Gate and authority
Identify decision maker and commitment requested.
02 ¦ Evidence pack
List approved or draft documents and versions.
03 ¦ Readiness tests
Review justification, ownership, scope, resources and exposure.
04 ¦ Critical conditions
Record mandatory gaps and whether they block progress.
05 ¦ Decision
Select Proceed, Conditional, Return or Stop with reasons.
06 ¦ Conditions and next gate
Assign actions, limits, owners, dates and G2 timing.
COMPLETION CHECK ¦ Use a critical-condition veto: missing authority, unsafe scope or an unowned mandatory safeguard cannot be offset by a high average checklist score. Conditional approval requires a clear limit on work allowed before conditions are met.
NEXT RECORD ¦ B1-B22 Planning toolkit

## B1 Schedule
B1 ¦ Project schedule and Gantt tracker
Sequence the work, preserve the baseline and forecast a credible finish.
02 ¦ PROJECT PLANNING | [7 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S08, Schedule Tracker; S03, slides 30-32. Scheduling context R03.
ID | Action / work package | Dependency IDs | Owner | Effort hours | Baseline start | Baseline finish | Actual start | Actual finish | Forecast finish | Complete % | Planned calendar days | Finish variance days | Status indicator | Progress evidence | Data check

## B2 Communications
B2 ¦ Project communications plan
Plan messages, channels and feedback around decisions and user needs.
02 ¦ PROJECT PLANNING |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S05, B2.
Audience | Purpose / message | Channel | Owner / approver | When | Feedback / evidence
USE THE RECORD ¦ What does this audience need to do? How will they ask a question? What can we say honestly while a decision is still pending? Do not promise consultation after the decision is already fixed. Protect personal or commercially sensitive information and use authorised branding. Low email response is not evidence of agreement.

## B3 Outputs
B3 ¦ Output description and acceptance specification
Define each deliverable so that production, testing and acceptance mean the same thing.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S05, B3 output descriptions.
01 ¦ Identity, purpose and user
Name output, objective, customer and operating owner.
02 ¦ Composition and format
Describe components, boundaries and delivery format.
03 ¦ Production capability
Specify skills, resources and production owner.
04 ¦ Quality and acceptance criteria
Define measurable conditions and mandatory safeguards.
05 ¦ Testing and review
State quality method, tester skills, evidence and authorised accepter.
06 ¦ Dependencies and control
Identify within-project, programme and external dependencies; record version approval.
COMPLETION CHECK ¦ "High quality" and "user friendly" are not sufficient acceptance criteria. Break broad expectations into observable conditions. A producer's self-declaration is not automatically independent acceptance.
NEXT RECORD ¦ B12 Quality / B13 Traceability / C19 Handover

## B4 Benefits
B4 ¦ Benefits realisation plan
Connect each intended benefit to changed practice, measurement and an accountable owner.
02 ¦ PROJECT PLANNING | [6 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S05, B4; S03, slide 28.
Benefit ID | Benefit / mechanism | Type | Unit | Baseline | Target | Actual | Progress to target | Baseline date | Review due | Benefit owner | Measurement method | Evidence | Interpretation

## B5 Transition
B5 ¦ Transition plan
Plan the move from temporary project delivery to sustained operation.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S05, B5; earlier S01 labels this B6. This edition follows S02/S05.
01 ¦ Outputs to transfer
List physical, digital, documentation and project-control outputs.
02 ¦ Acceptance and owner
State criteria, evidence and the authorised receiver.
03 ¦ Operating resources
Identify people, support, licences, access and capacity.
04 ¦ Knowledge and records
Specify user guidance, design records and archive responsibilities.
05 ¦ Schedule and fallback
Sequence cutover, stabilisation, support and rollback.
06 ¦ Risks and residuals
Record open items, receiving owners and transition approval.
COMPLETION CHECK ¦ A handover email is not evidence of operational readiness. Do not transfer unresolved work without a receiving owner, authority, resources and a due date. Keep project closure distinct from full benefit achievement.
NEXT RECORD ¦ C18 Cutover / C19 Handover / D7 Residuals

## B6 Contacts
B6 ¦ Project contact list
Maintain an accurate, purpose-limited directory of project roles and contact routes.
02 ¦ PROJECT PLANNING |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S07, contact checklist under D3; source discrepancy in S05 B6 recorded.
Function / role | Involved? | Contact | Business route | Deputy / escalation | Review date
USE THE RECORD ¦ Who is the right person for this decision or problem? Is the contact current? What personal information is genuinely necessary? Do not publish private phone numbers or sensitive stakeholder commentary without an appropriate basis. A contact list does not establish decision authority; refer to A4 for delegated decisions.

## B7 Work Breakdown
B7 ¦ Work breakdown structure
Decompose outputs into manageable work packages without losing the whole result.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Output hierarchy
Identify the project result and output families.
02 ¦ Work packages
Assign stable IDs and concise descriptions.
03 ¦ Boundary and owner
State inclusions, exclusions and accountable delivery owner.
04 ¦ Completion evidence
Specify the observable done condition.
05 ¦ Interfaces and omissions
Check dependencies, overlaps and missing control work.
06 ¦ Control links
Map package IDs to schedule, budget and quality records.
COMPLETION CHECK ¦ The WBS describes the full scope; sequencing comes afterwards. A package should be small enough to estimate and control, but not so detailed that updating it becomes the main project activity.
NEXT RECORD ¦ B1 Schedule / B9 Capacity / B10 Budget

## B8 Critical Path
B8 ¦ Dependency network and critical path
Understand the sequence that drives the earliest possible completion.
02 ¦ PROJECT PLANNING |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S03, slides 31-32; calculation by HR Delivery. Context R03.
ID | Duration | Predecessor | ES | EF | LS | LF | Float
USE THE RECORD ¦ Which branch controls the finish? What assumption gives another task float? Could the same resource being needed twice invalidate the apparent parallel work? The longest logical path is not a probability forecast. Hard date constraints, calendars, leads, lags and resource limits can change interpretation. The live B1 tracker does not automatically calculate this network.

## B9 Capacity
B9 ¦ Resource and capacity plan
Check that the plan fits the people, skills and time actually available.
02 ¦ PROJECT PLANNING |  |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Role / resource | Period | Work package | Demand hours | Available hours | Gap hours | Utilisation | Resolution / decision | Owner | Evidence

## B10 Budget
B10 ¦ Project budget and cost baseline
Create a complete, approved cost baseline linked to the work.
02 ¦ PROJECT PLANNING | [5 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S04, project costs and budget; HR Delivery calculation architecture.
Cost ID | Work package | Category | Unit / estimate basis | Quantity | Rate | Original baseline amount | Cost type | Cost owner | Estimate date | Source / approval evidence | Notes | Baseline integrity

## B11 RACI
B11 ¦ Responsibility assignment matrix (RACI)
Make ownership, delivery, consultation and information responsibilities unambiguous.
02 ¦ PROJECT PLANNING |  |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Output / decision | Sponsor | Project manager | HR Operations | IT Lead | Site managers | Finance | Other role | Accountability check | Delivery check

## B12 Quality Plan
B12 ¦ Quality and acceptance plan
Plan the tests and decisions that demonstrate fitness for purpose.
02 ¦ PROJECT PLANNING |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S04 PID quality and S05 output quality fields.
Test / output | Criterion | Method | Reviewer | Required by | Acceptance / evidence
USE THE RECORD ¦ What must pass before this is safe to use? Who can judge the result? Is time for rework actually in the schedule? Passing most tests is not enough when a critical test fails. Do not lower acceptance criteria simply to report completion. Any proposed change requires the appropriate owner and documented reasoning.

## B13 Traceability
B13 ¦ Requirements-to-acceptance traceability
Trace each requirement through design, delivery, testing and acceptance.
02 ¦ PROJECT PLANNING |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Requirement | Source / priority | Output | Acceptance criterion | Test / evidence | Status / accepter
USE THE RECORD ¦ Which requirement does this feature satisfy? What proves the requirement is met? Which requirement has no delivery owner or test? A link to a document is not evidence that its requirement has been satisfied. Preserve old IDs after a change and show supersession rather than deleting the audit trail.

## B14 Suppliers
B14 ¦ Procurement and supplier plan
Plan externally supplied work with clear specifications, approvals and acceptance.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Requirement and scope
Describe supplied outputs and acceptance criteria.
02 ¦ Route and authority
Record procurement method, approvers and rules.
03 ¦ Evaluation and cost
Specify criteria, whole-life costs and assumptions.
04 ¦ Milestones and dependencies
Plan mobilisation, inputs, reviews and deliverables.
05 ¦ Performance and safeguards
Define evidence, reporting, data access and escalation.
06 ¦ Handover and exit
Record support, records, access removal and final acceptance.
COMPLETION CHECK ¦ This is a planning record, not legal contract wording. Use approved contractual terms and qualified local advice where needed. Do not assume a penalty clause removes schedule risk.
NEXT RECORD ¦ C12 Supplier Review / D10 Release

## B15 Change Control
B15 ¦ Change-control procedure
Agree how requests to change the approved project baseline will be assessed and decided.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S06 C2 and S09; external context R02.
01 ¦ Change definition
Describe the boundary between clarification and change.
02 ¦ Request route
Specify form, log, required information and submitter.
03 ¦ Impact assessment
Name assessors and mandatory impact areas.
04 ¦ Authority and decision
State delegates, thresholds and decision categories.
05 ¦ Baseline update
Identify records to change, version control and communications.
06 ¦ Implementation verification
Confirm completion, evidence, closure and emergency review.
COMPLETION CHECK ¦ An approved request is not automatically implemented, and a logged request is not approval. Do not add pending cost requests to authorised budget. An emergency action still needs a traceable decision and review.
NEXT RECORD ¦ C2 Request / C2B Log / C10 Impact

## B16 Risk Workshop
B16 ¦ Risk workshop and response plan
Identify credible uncertainty and agree practical responses before it becomes an issue.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S03, slides 39-44 and S11 risk log.
01 ¦ Workshop scope and participants
Identify objectives, outputs and expertise represented.
02 ¦ Risk statements
Capture cause, event and effect without vague labels.
03 ¦ Assessment and controls
Record likelihood, impact, evidence and existing safeguards.
04 ¦ Response and owner
Select action, owner, date and authority.
05 ¦ Trigger and fallback
State early warning and the response if the event occurs.
06 ¦ Review and residual exposure
Set next review and evidence required before reassessment.
COMPLETION CHECK ¦ Risk scores prioritise discussion; they are not probabilities or monetary expected losses. A severe consequence may require escalation even at low likelihood. Planned mitigation does not justify lowering residual exposure until it is in place.
NEXT RECORD ¦ C4 Risk Log

## B17 Information
B17 ¦ Project information-handling plan
Define what information the project needs and how it will be controlled.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Information inventory
List categories, source and purpose.
02 ¦ Authority and minimisation
Record review, basis and minimum necessary detail.
03 ¦ Access and storage
Identify roles, approved location and version control.
04 ¦ Sharing and suppliers
Record transfers, restrictions and required agreements.
05 ¦ Retention and incidents
Set archive/disposal rules and escalation route.
06 ¦ Approval and change review
Name information owner, specialist checks and triggers.
COMPLETION CHECK ¦ Do not use live employee data merely because it is convenient for testing. Prefer suitable synthetic or de-identified test data where practical and approved. Do not treat spreadsheet protection as information security.
NEXT RECORD ¦ C17 Readiness / D9 Archive

## B18 Adoption Plan
B18 ¦ Adoption and learning plan
Prepare people to use the result correctly in their actual working conditions.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ User group and change
State the task or behaviour that changes.
02 ¦ Barriers and enablers
Identify capability, access, workload and workflow conditions.
03 ¦ Learning and support
Select practice, job aids, coaching and help routes.
04 ¦ Timing and ownership
Name delivery owner, manager role and learning dates.
05 ¦ Readiness evidence
Define what people must demonstrate before use.
06 ¦ Adoption follow-up
Plan observation, usage checks, feedback and support adjustment.
COMPLETION CHECK ¦ Do not report training attendance as adoption or use a single satisfaction score as proof of capability. Include employees who do not work standard office hours and check whether the new process increases avoidable burden.
NEXT RECORD ¦ C15 Adoption Tracker / C17 Readiness

## B19 Plan Challenge
B19 ¦ Planning assumptions challenge
Stress-test the assumptions hidden inside the proposed baseline.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Assumption under review
Identify the plan element and why it matters.
02 ¦ Evidence and confidence
Record evidence, uncertainty and gaps.
03 ¦ Challenge questions
Test turnaround, capacity, rework and interfaces.
04 ¦ Failure consequence
Describe cost, time, quality and benefit implications.
05 ¦ Resolution or test
Assign evidence gathering, contingency or a changed plan.
06 ¦ Gate recommendation
State whether the uncertainty is acceptable for approval.
COMPLETION CHECK ¦ Do not confuse a challenge session with personal criticism of the planner. Record uncertainty without penalising honest disclosure. The purpose is a more credible commitment, not an immaculate-looking plan.
NEXT RECORD ¦ B20 Scenarios / B21 Baseline Review

## B20 Scenarios
B20 ¦ Contingency and scenario plan
Prepare practical responses to plausible disruption without pretending to predict everything.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Scenario and trigger
Describe the event and evidence that activates review.
02 ¦ Affected commitments
Identify outputs, dates, costs and benefits.
03 ¦ Response options
Compare practical actions and trade-offs.
04 ¦ Resource and reserve
Estimate additional capacity, cost or time required.
05 ¦ Decision authority
Name approver and latest useful decision date.
06 ¦ Rehearsal and review
Record preparation, communication and update triggers.
COMPLETION CHECK ¦ Do not use reserve to conceal a knowingly infeasible baseline. Cost and time contingencies need owners and release rules. Never trade away a mandatory safeguard to protect a headline date.
NEXT RECORD ¦ C16 Recovery / C18 Rollback

## B21 Baseline Review
B21 ¦ Integrated baseline review
Check that scope, outputs, schedule, resources, costs and benefits describe one coherent project.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Baseline pack
List scope, PID, plan and register versions.
02 ¦ Scope-to-work trace
Confirm outputs and work-package coverage.
03 ¦ Schedule-to-resource trace
Check logic, capacity and realistic review time.
04 ¦ Cost and benefit trace
Confirm estimate completeness, affordability and benefit ownership.
05 ¦ Acceptance and transition
Check tests, rework, learning and operating readiness.
06 ¦ Findings and recommendation
Record gaps, decisions, conditions and G2 recommendation.
COMPLETION CHECK ¦ Approval of a collection of documents is not approval of a coherent plan. Record discrepancies and their resolution. Do not accept "we will sort it out during implementation" for a material missing commitment.
NEXT RECORD ¦ B22 G2

## B22 G2 Delivery Gate
B22 ¦ Gate 2: authorise implementation
Approve an integrated baseline and release a clearly bounded delivery commitment.
02 ¦ PROJECT PLANNING | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Authority and request
State funding, scope and implementation commitment.
02 ¦ Case and baseline evidence
Reference approved versions and integrated review.
03 ¦ Feasibility and ownership
Check capacity, suppliers, users and receiving owners.
04 ¦ Mandatory conditions
Verify safeguards, quality and information reviews.
05 ¦ Decision and tolerances
Record outcome, limits, reporting and change authority.
06 ¦ Conditions and next gates
Assign actions, readiness reviews and G3 expectations.
COMPLETION CHECK ¦ Sunk planning effort is not a reason to approve a weak case. Missing mandatory assurance or operating ownership blocks release. Conditional approval must specify which work may proceed and which work must wait.
NEXT RECORD ¦ C1-C21 Implementation toolkit

## C1 Progress Report
C1 ¦ Project progress report
Give the sponsor a truthful, decision-focused account of current delivery and forecast outcomes.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S06, C1 progress-report template; C5 source example treated separately.
01 ¦ Project and reporting basis
Record manager, sponsor, objective, period, status date and baseline.
02 ¦ Executive status and decision
State overall judgement, reasons and decision required.
03 ¦ Deliverables and dates
Show planned, forecast and accepted position; previous/current RAG where useful.
04 ¦ Issues, risks and dependencies
Identify material exposure, owner, action and escalation.
05 ¦ Cost and changes
Distinguish original budget, approved change, actual and forecast.
06 ¦ Highlights and next steps
Record evidence-based progress, next-period actions and decision deadlines.
COMPLETION CHECK ¦ RAG must follow agreed definitions and be accompanied by reasons. The workbook dashboard supplies indicators, not an automatic overall judgement. Missing data is not Green; a critical safeguard can make the project unacceptable despite good cost or schedule figures.
NEXT RECORD ¦ C5 Report Clinic / C7 Decisions / C16 Recovery
LINKED INDICATORS ¦ Reconcile these with the narrative above before releasing the report.
Original budget
Current approved budget
Complete forecast total
Forecast variance
Open issues | NO ISSUES ENTERED
High / Extreme open risks | NO RISKS ENTERED

## C2 Change Request
C2 ¦ Project change request
Present a proposed change and its consequences for an authorised decision.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S06, C2; S09 change-log fields. Context R02.
01 ¦ Identity and originator
Record CR ID, name, date, requester and contact route.
02 ¦ Description and reason
State the requested change and linked issue or requirement.
03 ¦ Scope and quality impact
Identify outputs and acceptance criteria affected.
04 ¦ Schedule and resource impact
Show affected tasks, capacity and forecast dates.
05 ¦ Budget impact
Separate one-off, recurring, internal and contingency implications.
06 ¦ Benefit and wider impact
Describe effects on benefits, users, data and related projects.
07 ¦ Rejection and alternatives
Explain what happens without approval and other options.
08 ¦ Decision and authority
Record recommendation, approver, outcome, date and evidence.
09 ¦ Implementation and verification
Name owner, baseline updates, test evidence and closure.
COMPLETION CHECK ¦ A change with no supplier invoice can still consume scarce internal capacity or delay benefits. "Essential" describes priority, not permission. Approval requires a named authorised decision maker and a traceable record.
NEXT RECORD ¦ C2B Change Log / C10 Impact

## C2B Change Log
C2B ¦ Project change log
Maintain one traceable register from change request to decision and verified implementation.
03 ¦ PROJECT IMPLEMENTATION | [8 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S09, Change Log; HR Delivery approval-integrity additions.
CR ID | Raised date | Description of change | Originator | Issue ID | Schedule impact days | Budget impact | Scope / quality impact | Related projects / benefits | Status | Decision / reasons | Decision maker | Decision date | Implemented date | Baseline version | Approval evidence | Approval completeness | Implementation evidence | Cost ID affected

## C3 Issues
C3 ¦ Project issues log
Record what has happened, agree a response and close it only when resolution is evidenced.
03 ¦ PROJECT IMPLEMENTATION | [6 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S10, Issue Log; S03, slides 39, 47-48.
Issue ID | Issue | Impact | Priority | Resolution action | Owner | Raised date | Escalated date | Resolve by | Closed date | Resolution evidence | Status | Age days | Overdue days

## C4 Risk Log
C4 ¦ Project risk log
Maintain a current view of uncertainty, controls, ownership and residual exposure.
03 ¦ PROJECT IMPLEMENTATION | [8 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S11, Risk Log; S03, slide 44 matrix.
Risk ID | Cause - event - effect | Impact if triggered | Impact 1-5 | Likelihood 1-5 | Score | Source matrix category | Proximity | Response | Management actions | Owner | Raised date | Last reviewed | Review due | Closed date | Residual impact | Residual likelihood | Residual category | Control / closure evidence

## C5 Report Review
C5 ¦ Project progress report: worked-report clinic
Review a draft report for internal consistency, evidence and decision usefulness.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S06, duplicate C1/C5 and worked example; HR Delivery review method.
01 ¦ Report identity
Record report date, period, version and reviewer.
02 ¦ Date and baseline checks
Test consistency of planned, actual and forecast dates.
03 ¦ Number reconciliation
Check budget, actual, forecast, changes and denominators.
04 ¦ Evidence and RAG
Review support for completion and status judgements.
05 ¦ Decision clarity
Identify decisions, owners, deadlines and consequences.
06 ¦ Corrections and approval
Record amendments, unresolved concerns and release decision.
COMPLETION CHECK ¦ A polished report with inconsistent dates or unsupported percentages is not reliable. Preserve adverse evidence and uncertainty. The source worked example has inconsistent reporting dates; this clinic treats consistency as a quality check rather than reproducing the error.
NEXT RECORD ¦ C1 Progress Report

## C6 Actions
C6 ¦ Project action log
Keep agreed actions visible from assignment to verified completion.
03 ¦ PROJECT IMPLEMENTATION | [5 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Action ID | Required result | Linked issue / risk / decision | Owner | Raised date | Original due | Current due | Status | Completed date | Completion evidence | Overdue days | Integrity

## C7 Decisions
C7 ¦ Project decision log
Preserve the reasoning, authority and consequences of material project decisions.
03 ¦ PROJECT IMPLEMENTATION |  |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Decision ID | Decision question | Options / evidence | Outcome | Decision maker | Decision date | Authority / evidence | Conditions | Action owner | Review trigger

## C8 Milestones
C8 ¦ Milestone and delivery review
Check whether accepted outputs and credible forecasts support the next commitment.
03 ¦ PROJECT IMPLEMENTATION |  |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Milestone ID | Accepted result required | Owner | Original date | Current approved date | Forecast date | Actual date | Evidence | Variance to original | Variance to current | Status

## C9 Cost Forecast
C9 ¦ Cost forecast and commitments
Forecast the total cost to complete without double counting money already spent or committed.
03 ¦ PROJECT IMPLEMENTATION | [5 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Cost ID | Description | Current line budget | Actual recognised | Unpaid committed | Other uncommitted ETC | Forecast at completion | Variance to current | Variance % | Owner | As-of date | Estimate / ledger evidence | Data check

## C10 Impact Assessment
C10 ¦ Integrated change-impact assessment
Test the full consequences of a change before recommending a decision.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Change boundary
State baseline versus proposed arrangement.
02 ¦ Delivery impact
Trace requirements, outputs, tasks, dates and resources.
03 ¦ Financial impact
Separate project, ongoing and internal cost implications.
04 ¦ User and information impact
Review burden, access, inclusion and safeguards.
05 ¦ Benefit and wider impact
Identify outcome timing, dependencies and related work.
06 ¦ Recommendation and control
Record option, conditions, authority and baseline updates.
COMPLETION CHECK ¦ Do not use "no impact" as a default. Record the reasoning or the owner who verified it. A change can be beneficial overall and still require mitigation for a particular group.
NEXT RECORD ¦ C2 Request / C2B Log

## C11 Tests and Defects
C11 ¦ Quality test and defect log
Record actual test results and control defects through retest and acceptance.
03 ¦ PROJECT IMPLEMENTATION | [5 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Test ID | Requirement / output | Expected result | Actual result | Mandatory? | Severity | Result | Correction owner | Retest due | Evidence | Accepted by | Acceptance date | Control status

## C12 Supplier Review
C12 ¦ Supplier performance review
Review supplied work against commitments, evidence and the project's actual needs.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Supplier and commitment
Identify supplied output, milestone and agreement reference.
02 ¦ Delivery and quality
Compare actual evidence with agreed criteria.
03 ¦ Internal inputs
Check access, information, review and decision dependencies.
04 ¦ Issues and recovery
Record corrective action, owner and due date.
05 ¦ Commercial implications
Identify payment, change or dispute matters for authorised review.
06 ¦ Review outcome
State accepted position, escalation and next review.
COMPLETION CHECK ¦ Do not accept or reject commercial claims outside delegated authority. A project performance log does not replace Procurement, Finance or legal review of contractual matters.
NEXT RECORD ¦ C3 Issues / C9 Forecast / D10 Release

## C13 Meetings
C13 ¦ Project team meeting and minutes
Run a meeting that produces decisions, resolves blockers and supports the team.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Meeting identity
Record purpose, date, attendees, authority and apologies.
02 ¦ Team and capacity check
Identify immediate constraints or support needs.
03 ¦ Exception review
Record material changes in actions, delivery and exposure.
04 ¦ Decisions
Link authorised decisions and escalations to C7.
05 ¦ Actions
Link result, owner and due date to C6.
06 ¦ Read-back and communication
Confirm commitments, unresolved concerns and distribution.
COMPLETION CHECK ¦ Do not let status reporting consume all the time needed for problem solving. Silence is not a commitment. Record sensitive personnel matters through the appropriate route, not open project minutes.
NEXT RECORD ¦ C6 Actions / C7 Decisions

## C14 Engagement Review
C14 ¦ Stakeholder engagement review
Check whether engagement is producing understanding, contribution and informed participation.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Group and expected contribution
State the role in delivery or use.
02 ¦ Reach and participation
Record who was involved and who was missed.
03 ¦ Understanding and concerns
Capture evidence and unresolved questions.
04 ¦ Barrier analysis
Identify workload, access, timing or design problems.
05 ¦ Response and owner
Agree action and communication back to the group.
06 ¦ Review of effect
Check whether understanding or participation improved.
COMPLETION CHECK ¦ Do not infer support from non-response. Small groups or identifiable comments need careful handling. Record concerns in neutral, specific language and explain how the project responded.
NEXT RECORD ¦ B2 Communications / C15 Adoption

## C15 Adoption Tracker
C15 ¦ Adoption and learning tracker
Track exposure, demonstrated capability and actual use as distinct results.
03 ¦ PROJECT IMPLEMENTATION | [5 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Group | Eligible | Invited | Attended | Demonstrated capability | Active users | Attendance rate | Demonstration rate | Active-use rate | Review period | Barrier / support | Owner | Count integrity

## C16 Recovery Plan
C16 ¦ Exception and recovery plan
Present a credible response when delivery is forecast to exceed authority or fail a material condition.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Exception and trigger
Identify the breached or forecast limit and evidence.
02 ¦ Cause and containment
Describe the mechanism and immediate protection.
03 ¦ Recovery options
Compare realistic alternatives and consequences.
04 ¦ Resource and feasibility
Test capacity, dependencies and assumptions.
05 ¦ Decision and new control
Record authority, approved response and baseline links.
06 ¦ Recovery monitoring
Set milestones, owners, evidence and stop conditions.
COMPLETION CHECK ¦ Do not promise an accelerated schedule without evidence of capacity and logic. Mandatory safeguards cannot be traded for date compliance. Repeated rebaselining is not proof of recovery.
NEXT RECORD ¦ C2 Change / C7 Decision / C1 Report

## C17 Readiness
C17 ¦ Pilot and release-readiness review
Decide whether the evidence supports a controlled pilot or wider release.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Release boundary
State pilot or rollout scope, users and date.
02 ¦ Readiness evidence
Review quality, process, people, information and support.
03 ¦ Mandatory conditions
Identify blockers and non-negotiable criteria.
04 ¦ Residual exposure
Record defects, risks, fallback and ownership.
05 ¦ Decision
State Go, Conditional Go, No Go or Return with authority.
06 ¦ Conditions and monitoring
Assign actions, evidence dates and stop triggers.
COMPLETION CHECK ¦ An 11/12 checklist result is not readiness if the missing item is mandatory. Conditional Go must define what may proceed and the condition that must be verified first. The workbook gate summary does not overrule the authorised decision.
NEXT RECORD ¦ C18 Cutover / C19 Acceptance

## C18 Cutover
C18 ¦ Go-live, cutover and rollback plan
Control the changeover so that service and safeguards remain protected.
03 ¦ PROJECT IMPLEMENTATION |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Step / time | Action | Owner | Checkpoint | Stop / fallback | Actual evidence
USE THE RECORD ¦ Who can stop cutover? What would make rollback necessary? Have we tested the fallback rather than merely written its name? Do not improvise changes outside the approved window or use rollback as a vague reassurance. Confirm data integrity, access and operational consequences with the relevant specialists.

## C19 Handover
C19 ¦ Operational handover and acceptance
Transfer accepted outputs with the knowledge, resources and accountability needed to operate them.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S05 B5, S07 D1 and S03 slides 54-57.
01 ¦ Output inventory
List outputs, versions and receiving owners.
02 ¦ Acceptance evidence
Reference criteria, test results and approvals.
03 ¦ Operating capability
Confirm people, support, access and maintenance.
04 ¦ Knowledge and records
Transfer guidance, design decisions and archive references.
05 ¦ Residual obligations
Assign open work, risk and issue owners with dates.
06 ¦ Acceptance and effective date
Record accepter, conditions, transfer date and remaining closure actions.
COMPLETION CHECK ¦ Acceptance of an output, transfer to operation and project closure are related but different decisions. Do not make the receiving owner accept an unmanageable backlog to protect the project's finish date.
NEXT RECORD ¦ C21 G3 / D1 Completion / D5 Sign-off

## C20 Benefits Review
C20 ¦ Benefits and business-case review
Check whether delivery still supports the intended value and whether the case remains justified.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Benefit and mechanism
Review the link between output, practice and result.
02 ¦ Evidence and comparison
Show baseline, actual, target, dates and denominators.
03 ¦ Adoption and disbenefits
Check use, burden, quality and unintended effects.
04 ¦ Cost and assumptions
Update ongoing cost and material case assumptions.
05 ¦ Judgement and action
Decide continue, adapt, investigate or stop recommendation.
06 ¦ Owner and follow-up
Assign operational action, review date and case update.
COMPLETION CHECK ¦ Pilot evidence is not proof of organisation-wide impact. Do not describe a target as achieved from a small or incomparable sample, or monetise capacity as cash without a separate realisation action.
NEXT RECORD ¦ A2 Case / D8 Ownership / D12 Review

## C21 G3 Closure Gate
C21 ¦ Gate 3: authorise closure preparation
Confirm that delivery and transition are sufficiently complete to begin formal close-down.
03 ¦ PROJECT IMPLEMENTATION | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Gate and authority
Identify G3 decision maker and request.
02 ¦ Delivery evidence
Review accepted outputs and remaining scope.
03 ¦ Operational readiness
Confirm support, capability, access and receiving owners.
04 ¦ Residual and financial position
Account for open work, exposure and commitments.
05 ¦ Benefit continuity
Verify owners, measures, dates and escalation.
06 ¦ Decision and closure actions
Record outcome, conditions and the G4 pack requirements.
COMPLETION CHECK ¦ G3 does not close the project; G4 records the formal end and transfer of accountability. Missing mandatory acceptance or an unowned operational obligation blocks progression.
NEXT RECORD ¦ D1-D14 Project close toolkit

## D1 Completion Report
D1 ¦ Project completion report
Account for delivery, performance, residual obligations and continuing benefits before formal closure.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Adapted from S07, D1; HR Delivery original/revised baseline comparison.
01 ¦ Purpose and delivered scope
Summarise objectives, changes and outputs.
02 ¦ Date performance
Compare original, current approved and actual completion.
03 ¦ Financial performance
Compare original/current budgets, actual spend and remaining liabilities.
04 ¦ Output acceptance
List physical, digital, documentation and project-control outputs with evidence.
05 ¦ Open risks, issues and actions
Record receiving owners, resources and due dates.
06 ¦ Transition and support
Confirm operating capability, records and effective ownership.
07 ¦ Overall project review
Record what worked, problems and what would change next time.
08 ¦ Benefits and follow-up
Distinguish realised, forecast and unachieved benefits.
09 ¦ Stakeholder comments and approval
Capture user views, reservations and closure authority.
COMPLETION CHECK ¦ Do not describe all objectives as met when some remain outstanding. Normal completion, conditional closure and premature termination require different explanations. A forecast amount must not be labelled final actual spend.
NEXT RECORD ¦ D14 G4

## D2 Lessons
D2 ¦ Lessons learnt record
Convert experience into a specific improvement that someone will actually adopt.
04 ¦ PROJECT CLOSE |  |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Original HR Delivery form developing S07 D2 heading and S03 closure learning.
Lesson ID | Event / evidence | Consequence | Explanation / limits | Future practice | Adoption action | Owner | Due date | Status | Adoption evidence

## D3 Stakeholder Handover
D3 ¦ Stakeholder management for successful implementation
Transfer the relationships, communication commitments and unresolved concerns needed for sustained use.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Retains S02/S07 D3 title; developed method by HR Delivery.
01 ¦ Continuing relationships
List groups and ongoing communication needs.
02 ¦ Open commitments
Record concerns, promises and unresolved feedback.
03 ¦ Receiving owners
Name operational relationship owners and deputies.
04 ¦ Contact and response route
Confirm approved channels and escalation.
05 ¦ Transition message
Explain what changes after closure and what remains open.
06 ¦ Verification
Check that stakeholders understand the new arrangement.
COMPLETION CHECK ¦ Do not transfer private stakeholder labels or unnecessary personal details. A closure message should be clear about what is complete and what is still under review, without implying unanimous support.
NEXT RECORD ¦ B6 Contacts / D8 Benefits / D14 G4

## D4 Strategy Handover
D4 ¦ Project managing the HR strategy implementation
Connect the completed project to the continuing HR strategy and portfolio of work.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Retains S02/S07 D4 title; original HR Delivery development.
01 ¦ Strategic linkage
Name objective, owner and intended contribution.
02 ¦ Delivered contribution
Identify accepted outputs and evidence.
03 ¦ Continuing actions
List operational work and benefit responsibilities.
04 ¦ Portfolio interfaces
Record dependencies and overlapping initiatives.
05 ¦ Next-work classification
Decide operation, existing initiative or new proposal.
06 ¦ Review and authority
Assign owners, dates and approval route for new work.
COMPLETION CHECK ¦ A project can contribute to a strategy without being solely responsible for the strategic outcome. Do not claim attribution beyond the evidence or roll remaining work into a vague phase two without approval.
NEXT RECORD ¦ A1 New Brief / D8 Benefits

## D5 Final Acceptance
D5 ¦ Final acceptance and sign-off
Obtain a clear, authorised acceptance decision for each final output and the operating package.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S05 B5 acceptance and S07 D1 approval.
01 ¦ Output and version
State exactly what is submitted for acceptance.
02 ¦ Criteria and evidence
Reference agreed tests and supporting records.
03 ¦ Exceptions
Identify defects or incomplete items and their significance.
04 ¦ Acceptance decision
Select Accepted, Conditional or Rejected with reasons.
05 ¦ Transfer and conditions
Record effective date, owner, resources and due dates.
06 ¦ Authorised sign-off
Name accepter, authority, date and evidence reference.
COMPLETION CHECK ¦ A signature does not cure missing evidence. Conditional acceptance must name the residual item, owner, due date and consequence of non-completion. Mandatory failures are not ordinary conditions.
NEXT RECORD ¦ D1 Completion / D14 G4

## D6 Final Costs
D6 ¦ Financial reconciliation and closure
Reconcile final expenditure, commitments and funding before closing the project account.
04 ¦ PROJECT CLOSE | [5 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
Cost ID | Category | Original budget | Approved changes | Current budget | Final actual | Variance to original | Variance to current | Remaining obligation | Finance evidence | Sign-off date | Closure check

## D7 Residual Transfer
D7 ¦ Residual risks, issues and actions transfer
Transfer remaining obligations explicitly rather than allowing them to disappear at closure.
04 ¦ PROJECT CLOSE |  |  |  |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Developed from S07 D1 open risks/issues and S05 B5 transition.
Original log ID | Type | Residual obligation | Consequence / controls | Closure blocker? | Receiving owner | Due / review date | Receiving record | Acceptance evidence | Accepted date | Transfer status

## D8 Benefits Handover
D8 ¦ Benefits ownership and follow-up
Secure the post-project review and action needed to realise intended benefits.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Benefit identity and status
State realised, forecast, partly realised or not yet measured.
02 ¦ Measurement continuity
Confirm baseline, target, population and data method.
03 ¦ Owner and resources
Name benefit owner, data owner and operational capacity.
04 ¦ Review and reporting
Set dates, forum and decision authority.
05 ¦ Remaining actions and risks
Record what must happen and what may prevent it.
06 ¦ Acceptance and escalation
Confirm ownership and the route for missed targets.
COMPLETION CHECK ¦ Do not change a target retrospectively to claim success. A benefits handover is not proof that the benefit will occur; it is an accountable arrangement for pursuing and evaluating it.
NEXT RECORD ¦ D12 Review / strategic performance forum

## D9 Archive
D9 ¦ Project archive and information disposal
Retain the evidence the organisation needs and remove unnecessary working material safely.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Record inventory
List final outputs, baselines, approvals and supporting evidence.
02 ¦ Retention decision
Classify keep, transfer, restrict or dispose under approved rules.
03 ¦ Archive control
Name owner, repository, naming and version standards.
04 ¦ Access and protection
Confirm permissions and confidential material handling.
05 ¦ Disposal evidence
Record approved removal of unnecessary copies.
06 ¦ Retrieval and sign-off
Test access and record information-owner approval.
COMPLETION CHECK ¦ This tool does not prescribe statutory retention periods. Confirm the actual rules and any hold requirements with the relevant owner. A workbook password is not an adequate archive-security strategy.
NEXT RECORD ¦ D14 G4 / operating record owner

## D10 Release
D10 ¦ Resource and supplier release
Release people, access, contracts and facilities without losing essential support.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Resource inventory
List people, suppliers, facilities, licences and access.
02 ¦ Release readiness
Confirm acceptance, handover and support conditions.
03 ¦ Transfer or end
Decide what continues in operation and what stops.
04 ¦ Actions and authority
Assign return, cancellation, removal and settlement actions.
05 ¦ Knowledge protection
Confirm documentation and capability transfer before departure.
06 ¦ Verification
Record completed release, evidence and continuing obligations.
COMPLETION CHECK ¦ Do not end supplier or staff support before operating readiness is established. Contract termination and payment decisions follow authorised organisational processes; this checklist does not create that authority.
NEXT RECORD ¦ D6 Costs / D9 Archive / D14 G4

## D11 Closure Workshop
D11 ¦ Project closure and learning workshop
Bring delivery and receiving owners together to agree the closure position and usable lessons.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Purpose and evidence pack
Record participants, decision boundary and documents.
02 ¦ Performance review
Compare commitments, changes and delivered results.
03 ¦ Experience and learning
Capture evidence-based strengths and problems.
04 ¦ Residual and benefit transfer
Confirm continuing owners and commitments.
05 ¦ Closure recommendation
Record conditions and matters for formal approval.
06 ¦ Actions and follow-up
Assign lesson adoption and post-project reviews.
COMPLETION CHECK ¦ Avoid a blame session or a ceremonial success presentation. Evidence and respectful challenge can coexist. Record minority views and unresolved concerns rather than forcing artificial consensus.
NEXT RECORD ¦ D2 Lessons / D14 G4

## D12 Post Review
D12 ¦ Post-implementation review
Evaluate operating use and benefits after enough time has passed to observe them.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Review question and period
State purpose, timing and accountable review owner.
02 ¦ Evidence and method
Define data, population, comparison and limitations.
03 ¦ Results
Show baseline, target, actual and balancing measures.
04 ¦ Interpretation
Consider adoption, other changes and plausible contribution.
05 ¦ Decision and action
Agree operating improvement, further enquiry or new proposal.
06 ¦ Follow-up
Assign owners, dates and the next evidence check.
COMPLETION CHECK ¦ Before-and-after change alone does not prove causation. Do not retrospectively redefine success or use a small convenience sample as a population estimate. Escalate serious harm or control failures immediately rather than waiting for the scheduled review.
NEXT RECORD ¦ D8 Benefits / A1 New Proposal

## D13 Early Close
D13 ¦ Premature closure and stop decision
End or pause a project responsibly when its case, feasibility or conditions no longer justify continuation.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Stop or pause rationale
Describe the changed case, feasibility or mandatory condition.
02 ¦ Options and future consequences
Compare remaining cost, value and risk.
03 ¦ Immediate safeguards
Identify protection and continuity actions.
04 ¦ Outputs and obligations
List usable work, commitments and residual exposure.
05 ¦ Authorised decision
Record authority, reasons, conditions and communication.
06 ¦ Controlled exit or restart
Assign closure actions or explicit restart criteria.
COMPLETION CHECK ¦ Do not continue solely because substantial money has already been spent. Equally, do not abandon legal, contractual, safety or information obligations when stopping. Obtain appropriate specialist advice for those obligations.
NEXT RECORD ¦ D1 Completion / D14 G4 / A1 new project

## D14 G4 Final Gate
D14 ¦ Gate 4: close and transfer accountability
Formally end the project with accepted records and explicit continuing responsibilities.
04 ¦ PROJECT CLOSE | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
HR Delivery development
01 ¦ Closure type and authority
State normal, conditional or premature closure and decision maker.
02 ¦ Completion and acceptance
Reference delivered scope, criteria and sign-off.
03 ¦ Financial and residual assurance
Confirm liabilities, transferred exposure and owners.
04 ¦ Benefits and learning
Verify future reviews and adopted improvement actions.
05 ¦ Archive and release
Confirm records, access, people and supplier arrangements.
06 ¦ Formal decision
Record outcome, date, conditions and continuing accountability.
COMPLETION CHECK ¦ A conditional closure must be bounded and explicitly permitted by the sponsor's authority. Do not use it to disguise an unaccepted core output. The final decision remains a human governance judgement, not the workbook's checklist percentage.
NEXT RECORD ¦ Operational ownership / scheduled benefit reviews

## B1 Gantt
B1 ¦ LINKED WEEKLY SCHEDULE VIEW
Calendar-day view only. Baselines are B; forecast/actual footprint is F; both is BF. Dates remain in B1 Schedule.
02 ¦ PROJECT PLANNING | [6 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
ID | Action | Owner | Baseline start | Baseline finish | Forecast / actual finish | Status

## EX Case
EX ¦ PROJECT READY - FICTIONAL TEACHING CASE
These values never feed the live project forms or dashboard. Dates are hypothetical teaching dates.
HR DELIVERY ¦ PRACTITIONER WORKBOOK |  | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
RIWAQ TECHNICAL SERVICES 600 employees ¦ 4 sites ¦ 24 line managers Purpose: consistent onboarding through the existing platform. No payroll, grading or immigration-policy redesign.
Business outcome | Raise day-one readiness from 62% to 90% by 5 August 2027.
Baseline | 62 ready starters out of 100 recent starters. This is the fictional project's baseline, not an external benchmark.
Six outputs | Process; role checklist; configured workflow; learning kit; pilot report; operating handover.
Original commitment | Start 11 January 2027; planned close 29 April 2027; original budget SAR 240,000.
Approved change | CR01 adds SAR 12,000 and seven calendar days. Approved on 10 March; current budget SAR 252,000 and close 6 May.
12 March snapshot | Actual SAR 148,000 + unpaid commitments SAR 66,000 + other ETC SAR 44,000 = forecast SAR 258,000.
Final position | Actual close 6 May 2027; final recognised cost SAR 248,000. Compare with both original and current approved baselines.
Outcome evidence | Pilot: 17/20 ready = 85%. First post-rollout review: 86/100 = 86%. The 90% target is not yet met.
Learning evidence | 20 pilot managers eligible; 18 attended; 17 demonstrated competence. Attendance and demonstration are separate measures.
Benefits boundary | Estimated 800 annual capacity hours = 200 starters x four hours. These are not cash savings. Ongoing cost SAR 18,000/year is separate.
Governance | G1 22 January; G2 5 February; CR01 linked to IS02; four gates retain human decision authority.
Future review | The August review is scheduled, not invented. HR Operations owns measurement after project closure.

## EX Calculations
EX ¦ WORKED CALCULATIONS
Editable fictional inputs with transparent formulas. This sheet is isolated from the live dashboard.
HR DELIVERY ¦ PRACTITIONER WORKBOOK | [6 empty] | OPEN TOOL INDEX
BLUE text / pale-blue cells: enter your evidence. BLACK text / pale-teal cells: calculated. Blank is not zero or approval.
Category | Original | Approved delta | Current | Actual at 12 Mar | Unpaid committed | Other ETC | Forecast | Final actual | Final vs current
Advisory | 80000 | 0 | 80000 | 55000 | 20000 | 7000 | 82000 | 82000 | 2000
Configuration | 90000 | 12000 | 102000 | 64000 | 40000 | 4000 | 108000 | 103000 | 1000
Learning | 30000 | 0 | 30000 | 16000 | 6000 | 12000 | 34000 | 34000 | 4000
Internal capacity | 25000 | 0 | 25000 | 13000 | 0 | 11000 | 24000 | 29000 | 4000
Controlled reserve | 15000 | 0 | 15000 | 0 | 0 | 10000 | 10000 | 0 | -15000
TOTAL | 240000 | 12000 | 252000 | 148000 | 66000 | 44000 | 258000 | 248000 | -4000
Forecast vs current % |  |  | 2.381% |  |  | Final vs original % |  |  | 3.333%
Readiness measure | Ready | Eligible | Rate | Interpretation |  | Target | 90%
Baseline | 62 | 100 | 62% | Starting position
Pilot | 17 | 20 | 85% | Not a population estimate |  | Target attainment progress | 85.71%
First post-rollout | 86 | 100 | 86% | Target not yet met
INTERPRETATION ¦ 86% readiness is 24 percentage points above the 62% baseline, but remains four percentage points below the 90% target. Progress through the baseline-to-target gap is a different number; it is not the readiness rate.
Activity | Duration days | Predecessors | Early start | Early finish | Late start | Late finish | Total float | Critical?
A | 3 | - | 0 | 3 | 0 | 3 | 0 | Yes
B | 5 | A | 3 | 8 | 3 | 8 | 0 | Yes
C | 4 | A | 3 | 7 | 4 | 8 | 1 | No
D | 6 | B,C | 8 | 14 | 8 | 14 | 0 | Yes
E | 4 | D | 14 | 18 | 14 | 18 | 0 | Yes
F | 2 | E | 18 | 20 | 18 | 20 | 0 | Yes
FIXED TEACHING NETWORK ¦ Elapsed-day positions start at zero. Critical path A-B-D-E-F = 20 days; C has one day of float. Edit durations to explore this specific network only; predecessor labels are documentary, while formulas encode the shown fixed dependencies. This is not the live project schedule engine.
Option | Mandatory pass? | Benefit | Delivery | Affordability | Manageable risk | Weighted score
|  | 35% | 25% | 20% | 20%
Do nothing | No | 1 | 3 | 5 | 2 | 2.5
Manual repair | Yes | 3 | 4 | 4 | 3 | 3.45
Phased workflow | Yes | 5 | 4 | 3 | 4 | 4.15
Full replacement | No | 4 | 2 | 1 | 2 | 2.5
OPTIONS ¦ Scores illustrate the arithmetic for every option, including ineligible options. The live A8 tool suppresses a numerical recommendation when the mandatory condition is not passed. Equal scores do not mean equal risks, costs or consequences.
Impact | Likelihood | Product | Category |  | RISK INTERPRETATION A 5 x 1 score falls in Moderate in the source matrix. That must not hide a catastrophic consequence. Examine mandatory safeguards and escalate severity separately. Ordinal products do not estimate probability or financial expected loss.
1 | 1 | 1 | Low
2 | 3 | 6 | Moderate
3 | 4 | 12 | High
4 | 4 | 16 | Extreme
5 | 1 | 5 | Moderate